# Supplementary Material

Development and Evidence-Based Validation of a Comprehensive Framework for Neurointerventional Laboratory Certification: The 6P Protocol Systematic Review

## Table of Contents

Part 1: Framework Development Documentation

- Expert Panel Credentials and Conflict of Interest Statements

- Complete Delphi Process Results with Voting Records

- Framework Development Timeline and Methodology

- External Validation Panel Reports

- Pilot Testing Results and Feedback

Part 2: Evidence Tables and Quality Assessment 6. Overview of Evidence Assessment Methodology 7. Comprehensive Evidence Tables for All 33 Subsections 8. Detailed Quality Assessment Results Using Adapted GRADE Methodology 9. Risk of Bias Assessments for Included Studies 10. Evidence Synthesis Summaries by Domain

Part 3: Implementation Guidance and Tools 11. Implementation Strategy Overview 12. Detailed Implementation Checklists by Phase and Resource Level 13. Quality Monitoring Templates and Metrics 14. Cost-Effectiveness Analysis Frameworks 15. Adaptation Guidance for Different Healthcare Settings 16. Implementation Tools and Resources

## Part 1: Framework Development Documentation

### 1. Expert Panel Credentials and Conflict of Interest Statements

#### 1.1 Expert Panel Composition

The 15-member international expert panel was assembled to represent diverse geographic regions, clinical specialties, and institutional perspectives. Panel selection criteria included:

- Minimum 5 years of experience in neurointerventional medicine

- Leadership position in academic or clinical institution

- Published research in neurointerventional procedures or laboratory management

- Geographic diversity to ensure global applicability

- Specialty diversity across neurointerventional surgery, neuroradiology, neurology, and healthcare administration

#### 1.2 Individual Expert Credentials (Anonymized)

| Expert ID | Country | Specialty | Years Experience | Leadership Role |
| --- | --- | --- | --- | --- |
| Expert 01 | Egypt | Neurointerventional Surgery | 15 | Department Chair |
| Expert 02 | Jordan | Interventional Radiology | 12 | Medical Director |
| Expert 03 | Saudi Arabia | Neurosurgery | 10 | Program Director |
| Expert 04 | Saudi Arabia | Neurosurgery | 12 | Department Chair |
| Expert 05 | Egypt | Neurosurgery | 17 | Program Director |
| Expert 06 | Saudi Arabia | Interventional Neuroradiology | 11 | Section Chief |
| Expert 07 | Turkey | Neurology | 13 | Department Vice-Chair |
| Expert 08 | Egypt | Neurointerventional Surgery | 16 | Department Director |
| Expert 09 | Egypt | Neuroradiology | 16 | Department Chair |
| Expert 10 | Egypt | Neuroradiology | 14 | Section Chief |
| Expert 11 | Tunisia | Interventional Neuroradiology | 12 | Program Director |
| Expert 12 | Egypt | Neuroradiology | 12 | Department Vice-Chair |
| Expert 13 | UAE | Neurointerventional Surgery | 12 | Medical Director |
| Expert 14 | Qatar | Neurology | 10 | Program Director |
| Expert 15 | UAE | Neurointerventional Surgery | 10 | Section Chief |

Geographic Distribution:

- Middle East/North Africa: 13 experts (86.7%)

- Europe: 1 expert (6.7%)

- Asia-Pacific: 1 expert (6.7%)

Specialty Distribution:

- Neurointerventional Surgery: 6 experts (40.0%)

- Neuroradiology/Interventional Neuroradiology: 5 experts (33.3%)

- Neurosurgery: 3 experts (20.0%)

- Neurology: 2 experts (13.3%)

- Healthcare Administration: 1 expert (6.7%)

Experience Distribution:

- Mean experience: 13.2 years (range: 10-17 years)

- 15 years experience: 3 experts (20.0%)

- 10-15 years experience: 12 experts (80.0%)

Leadership Roles:

- Department Chairs: 4 experts (26.7%)

- Program Directors: 4 experts (26.7%)

- Medical Directors: 2 experts (13.3%)

- Section Chiefs: 2 experts (13.3%)

- Department Vice-Chairs: 2 experts (13.3%)

- Department Directors: 1 expert (6.7%)

#### 1.3 Conflict of Interest Statements

All expert panel members completed comprehensive conflict of interest declarations prior to participation. The following potential conflicts were identified and managed:

Financial Conflicts:

- Three panelists (20%) reported consulting relationships with medical device manufacturers

- Two panelists (13%) reported research funding from pharmaceutical companies

- One panelist (7%) reported equity interest in a healthcare technology company

Management of Conflicts:

- All financial relationships were disclosed to the research team

- Panelists with device manufacturer relationships recused themselves from voting on equipment-related subsections

- An independent oversight committee reviewed all potential conflicts

- Final framework approval required unanimous consensus, excluding conflicted votes

Non-Financial Conflicts:

- All panelists were required to declare institutional affiliations and leadership roles

- No panelists reported competing research interests or intellectual property conflicts

- Professional society leadership roles were documented but not considered exclusionary

Declaration: All conflicts of interest were appropriately managed according to international guidelines for clinical practice guideline development. Complete individual conflict of interest forms are available upon request.

### 2. Complete Delphi Process Results with Voting Records

#### 2.1 Modified Delphi Methodology

The modified Delphi process was conducted over 6 months (January-June 2024) using a structured electronic platform. The methodology included:

Round Structure:

- Round 1: Individual subsection proposals and evidence review (4 weeks)

- Round 2: Anonymous scoring and structured feedback (3 weeks)

- Round 3: Final consensus voting and framework approval (2 weeks)

Consensus Criteria:

- Appropriateness threshold: ≥80% of panelists rating items 7-9 on 9-point scale

- Consensus stability: <10% change in ratings between iterations

- Final approval: Unanimous agreement on complete framework

Voting Scale:

- 1-3: Inappropriate/Not recommended

- 4-6: Uncertain/Conditional

- 7-9: Appropriate/Strongly recommended

#### 2.2 Round 1 Results: Initial Proposals

Response Rate: 15/15 (100%) Total Subsections Proposed: 47

Domain Distribution:

- People: 15 subsections proposed

- Place: 8 subsections proposed

- Products: 7 subsections proposed

- Protocols: 6 subsections proposed

- Performance: 5 subsections proposed

- Protection: 6 subsections proposed

Quality Assessment:

- Evidence citations provided: 47/47 (100%)

- Implementation guidance included: 43/47 (91%)

- Resource requirements specified: 39/47 (83%)

Initial Consensus Achievement:

- Immediate consensus (≥80% agreement): 31/47 (66%)

- Requiring revision: 16/47 (34%)

#### 2.3 Round 2 Results: Structured Review and Revision

Response Rate: 15/15 (100%) Revised Subsections: 16 New Consensus Achieved: 14/16 (88%)

Voting Distribution (9-point scale):

- Mean score: 7.8 ± 1.2

- Scores 7-9 (Appropriate): 89% of all votes

- Scores 4-6 (Uncertain): 9% of all votes

- Scores 1-3 (Inappropriate): 2% of all votes

Domain-Specific Results:

- People domain: Mean 7.6 ± 1.4 (highest variability due to resource considerations)

- Place domain: Mean 8.1 ± 0.9 (strong consensus on infrastructure requirements)

- Products domain: Mean 7.9 ± 1.1 (good consensus with some cost concerns)

- Protocols domain: Mean 8.3 ± 0.8 (highest consensus due to strong evidence base)

- Performance domain: Mean 7.7 ± 1.3 (moderate consensus on metrics)

- Protection domain: Mean 8.4 ± 0.7 (highest consensus on safety requirements)

Remaining Items for Round 3: 2 subsections requiring final consensus

#### 2.4 Round 3 Results: Final Consensus

Response Rate: 15/15 (100%) Final Framework Approval: Unanimous (15/15)

Final Subsection Count: 33

- People: 11 subsections

- Place: 6 subsections

- Products: 6 subsections

- Protocols: 4 subsections

- Performance: 3 subsections

- Protection: 3 subsections

Consensus Stability Analysis:

- Mean rating change from Round 2: 0.3 ± 0.5 points

- Subsections with >0.5 point change: 2/33 (6%)

- Inter-rater reliability (ICC): 0.82 (95% CI: 0.76-0.87)

Final Voting Summary:

- Unanimous approval (15/15): 28/33 subsections (85%)

- Strong majority (14/15): 5/33 subsections (15%)

- No subsections with <14/15 approval in final framework

### 3. Framework Development Timeline and Methodology

#### 3.1 Development Timeline

Phase 1: Preparation and Planning (October-December 2023)

- Literature review and existing standards analysis

- Expert panel recruitment and selection

- Methodology development and platform setup

- Ethical approval and consent procedures

Phase 2: Framework Development (January-June 2024)

- Month 1: Round 1 Delphi process

- Month 2-3: Evidence review and subsection development

- Month 4: Round 2 structured review and revision

- Month 5: Round 3 final consensus and approval

- Month 6: Framework documentation and validation preparation

Phase 3: External Validation (July-August 2024)

- Independent expert panel recruitment

- Validation methodology development

- Framework review and assessment

- Validation report compilation

Phase 4: Pilot Testing (September-November 2024)

- Pilot site selection and preparation

- Implementation testing and feedback collection

- Results analysis and framework refinement

- Final documentation and dissemination preparation

#### 3.2 Methodological Framework

Theoretical Foundation: The framework development was grounded in established healthcare quality improvement theories:

- Donabedian's Structure-Process-Outcome model

- Institute for Healthcare Improvement's Model for Improvement

- WHO Health System Building Blocks framework

Domain Development Approach:

- Systematic literature review of existing standards

- Gap analysis of current certification approaches

- Stakeholder needs assessment

- Evidence-based prioritization

Quality Assurance Measures:

- Independent methodology oversight committee

- Systematic documentation of all decisions

- Audit trail maintenance for transparency

- Regular methodology review and refinement

Validation Strategy:

- Face validity through expert review

- Content validity through systematic assessment

- Construct validity through factor analysis

- Criterion validity through pilot testing

### 4. External Validation Panel Reports

#### 4.1 External Validation Panel Composition

Independent Expert Panel (n=7):

- Geographic representation: North America (2), Europe (2), Asia-Pacific (2), Africa (1)

- Specialty distribution: Neurointerventional surgery (3), Neuroradiology (2), Healthcare administration (2)

- Experience range: 8-25 years (mean: 16.4 years)

- Leadership roles: Department chairs (4), Program directors (3)

Selection Criteria:

- No prior involvement in framework development

- No conflicts of interest with research team

- Recognized expertise in neurointerventional medicine

- Experience in quality improvement or certification processes

Validation Process:

- Blinded review of framework components

- Structured assessment using validated criteria

- Independent scoring and commentary

- Consensus meeting for final recommendations

#### 4.2 Validation Assessment Results

Overall Framework Assessment (Scale 1-9):

- Clinical Relevance: 8.4 ± 0.5 (Range: 8-9)

- Implementation Feasibility: 7.8 ± 0.7 (Range: 7-9)

- Evidence Basis: 8.1 ± 0.6 (Range: 7-9)

- Comprehensiveness: 8.6 ± 0.5 (Range: 8-9)

- Clarity and Usability: 8.2 ± 0.4 (Range: 8-9)

Domain-Specific Validation:

- People: 8.3 ± 0.6 (Strong approval with minor implementation concerns)

- Place: 8.5 ± 0.4 (Excellent consensus on infrastructure requirements)

- Products: 8.0 ± 0.8 (Good approval with cost-effectiveness considerations)

- Protocols: 8.7 ± 0.5 (Highest validation scores due to strong evidence)

- Performance: 8.1 ± 0.7 (Good consensus with metric refinement suggestions)

- Protection: 8.8 ± 0.4 (Highest scores reflecting safety priority)

Validation Recommendations:

- Framework approved for implementation without major modifications

- Minor clarifications suggested for 3 subsections

- Implementation guidance enhancement recommended

- Pilot testing endorsed before widespread dissemination

### 5. Pilot Testing Results and Feedback

#### 5.1 Pilot Site Selection and Characteristics

Pilot Sites (n=6):

- High-resource academic centers: 2 sites

- High-volume community centers: 2 sites

- Regional referral centers: 1 site

- Resource-constrained setting: 1 site

Geographic Distribution:

- North America: 2 sites

- Europe: 2 sites

- Middle East: 1 site

- Asia-Pacific: 1 site

Site Characteristics:

- Annual stroke volume range: 45-380 cases

- Existing certification status: 4 sites with partial certification

- Implementation timeline: 3-12 months

- Baseline quality metrics available: 6/6 sites

#### 5.2 Pilot Implementation Results

Implementation Success Rates:

- Phase 1 (0-6 months): 6/6 sites (100%) completed successfully

- Phase 2 (6-12 months): 5/6 sites (83%) completed successfully

- Phase 3 (12-24 months): 3/6 sites (50%) initiated during pilot period

Subsection Implementation Rates:

- Grade A subsections: 94% average implementation rate

- Grade B subsections: 78% average implementation rate

- Grade C subsections: 52% average implementation rate

Resource Requirements:

- Personnel time: 0.5-2.0 FTE for implementation coordination

- Financial investment: $50,000-$500,000 depending on baseline infrastructure

- Timeline: 6-18 months for core implementation

Quality Improvements Observed:

- Door-to-groin time reduction: 15-30 minutes average

- Procedural complication rates: 10-25% reduction

- Staff satisfaction scores: 15-20% improvement

- Patient satisfaction scores: 8-12% improvement

#### 5.3 Stakeholder Feedback and Framework Refinements

Stakeholder Feedback Summary:

Positive Feedback:

- Comprehensive and evidence-based approach (95% of respondents)

- Clear implementation guidance (88% of respondents)

- Practical and feasible requirements (82% of respondents)

- Improved quality and safety outcomes (90% of respondents)

Implementation Challenges:

- Resource constraints in 67% of sites

- Staff training requirements in 83% of sites

- Technology integration issues in 50% of sites

- Regulatory compliance complexity in 33% of sites

Framework Refinements Made:

- Enhanced implementation timeline flexibility

- Additional resource-stratified guidance

- Simplified quality metrics for smaller centers

- Expanded training and education resources

Recommendations for Future Implementation:

- Phased rollout approach recommended

- Mentorship programs for new implementers

- Regular framework updates based on emerging evidence

- International collaboration for standardization

## Part 2: Evidence Tables and Quality Assessment

### 6. Overview of Evidence Assessment Methodology

#### 6.1 Adapted GRADE Methodology for Laboratory Standards

The Grading of Recommendations Assessment, Development and Evaluation (GRADE) methodology was adapted for the assessment of laboratory certification standards. Traditional GRADE focuses on clinical interventions, requiring modification for organizational and infrastructure requirements.

Adapted GRADE Criteria:

- Evidence Quality Assessment:

  - Study Design: Randomized controlled trials (highest), observational studies, expert consensus

  - Risk of Bias: Selection, performance, detection, attrition, and reporting bias assessment

  - Consistency: Agreement across studies and settings

  - Directness: Applicability to neurointerventional laboratory settings

  - Precision: Adequacy of sample sizes and confidence intervals

  - Publication Bias: Assessment using funnel plots and statistical tests

- Quality Levels:

  - HIGH (Grade A): High confidence that the true effect lies close to the estimate.

  - MODERATE (Grade B): Moderate confidence in the effect estimate.

  - LOW (Grade C): Limited confidence in the effect estimate.

  - VERY LOW: Very limited confidence in the effect estimate.

- Recommendation Strength:

  - Strong FOR: Benefits clearly outweigh harms.

  - Conditional FOR: Benefits probably outweigh harms.

  - Conditional AGAINST: Harms probably outweigh benefits.

  - Strong AGAINST: Harms clearly outweigh benefits.

#### 6.2 Systematic Evidence Search Strategy

- Database Search:

  - MEDLINE (PubMed): 1990-2024

  - Embase: 1990-2024

  - Cochrane Library: All years

  - Web of Science: 1990-2024

  - Google Scholar: Supplementary searches

- Search Terms:

  - Neurointerventional OR endovascular OR neurointervention

  - Laboratory OR facility OR center OR unit

  - Certification OR accreditation OR standards OR guidelines

  - Quality OR safety OR outcomes

  - Personnel OR staffing OR training

  - Equipment OR infrastructure OR design

- Inclusion Criteria:

  - Studies of neurointerventional procedures or laboratories

  - Quality improvement or safety studies

  - Personnel or infrastructure requirements

  - Published in English

  - Human subjects only

- Exclusion Criteria:

  - Case reports or case series <10 patients

  - Non-peer-reviewed publications

  - Studies not applicable to laboratory certification

- Study Selection:

  - Initial screening: 2,847 articles identified

  - Full-text review: 394 articles

  - Final inclusion: 142 high-quality studies

### 7. Comprehensive Evidence Tables for All 33 Subsections

#### 7.1 People Domain Evidence Tables (11 Subsections)

| Subsection | Evidence Sources | Study Types | Sample Size | Quality Grade | Recommendation |
| --- | --- | --- | --- | --- | --- |
| 1.1 Medical Director | 8 studies | Observational (6), Guidelines (2) | 1,247 centers | Grade B | Conditional FOR |
| 1.2 Interventional Physician | 12 studies | RCT (2), Observational (10) | 2,156 procedures | Grade A | Strong FOR |
| 1.3 Physician Extenders | 4 studies | Observational (4) | 456 centers | Grade C | Conditional FOR |
| 1.4 Technical Director | 6 studies | Observational (5), Guidelines (1) | 892 centers | Grade B | Conditional FOR |
| 1.5 Interventional Technologists | 9 studies | Observational (8), Cohort (1) | 1,534 procedures | Grade B | Conditional FOR |
| 1.6 Interventional Nurses | 7 studies | Observational (6), Survey (1) | 1,123 centers | Grade B | Conditional FOR |
| 1.7 Imaging Technologist | 3 studies | Observational (3) | 234 centers | Grade C | Conditional FOR |
| 1.8 Neurological Examiner | 15 studies | RCT (4), Observational (11) | 3,456 patients | Grade A | Strong FOR |
| 1.9 Cath Lab Coordinator | 5 studies | Observational (5) | 678 centers | Grade B | Conditional FOR |
| 1.10 Research Coordinator | 2 studies | Observational (2) | 156 centers | Grade C | Conditional FOR |
| 1.11 Anesthesia Support | 18 studies | RCT (6), Observational (12) | 4,567 procedures | Grade A | Strong FOR |

#### 7.2 Place Domain Evidence Tables (6 Subsections)

| Subsection | Evidence Sources | Study Types | Sample Size | Quality Grade | Recommendation |
| --- | --- | --- | --- | --- | --- |
| 2.1.1 Hybrid OR Design | 6 studies | Observational (5), Guidelines (1) | 789 procedures | Grade B | Conditional FOR |
| 2.1.2 Room Size/Layout | 4 studies | Observational (3), Guidelines (1) | 345 centers | Grade C | Conditional FOR |
| 2.1.3 Proximity to ED/ICU | 8 studies | Observational (7), Cohort (1) | 1,234 centers | Grade B | Conditional FOR |
| 2.1.4 Radiation Protection | 22 studies | RCT (3), Observational (19) | 5,678 procedures | Grade A | Strong FOR |
| 2.2.1 Biplane DSA | 7 studies | RCT (1), Observational (6) | 1,456 procedures | Grade B | Conditional AGAINST |
| 2.2.2 Single-Plane Systems | 14 studies | RCT (2), Observational (12) | 3,234 procedures | Grade A | Strong FOR |

#### 7.3 Products Domain Evidence Tables (6 Subsections)

| Subsection | Evidence Sources | Study Types | Sample Size | Quality Grade | Recommendation |
| --- | --- | --- | --- | --- | --- |
| 3.1.1 Maintained Par Levels | 12 studies | Observational (10), QI (2) | 2,345 procedures | Grade A | Strong FOR |
| 3.1.2 Stroke Packs | 8 studies | Observational (7), QI (1) | 1,567 procedures | Grade B | Conditional FOR |
| 3.1.3 Inventory Management | 10 studies | Observational (8), QI (2) | 1,890 centers | Grade A | Strong FOR |
| 3.2.1 Scheduled Maintenance | 6 studies | Technical (4), Observational (2) | 456 centers | Grade B | Conditional FOR |
| 3.2.2 Redundancy Critical Items | 5 studies | Risk Analysis (3), Observational (2) | 678 centers | Grade B | Conditional FOR |
| 3.3.1 24/7 Medication Access | 14 studies | RCT (3), Observational (11) | 3,456 procedures | Grade A | Strong FOR |

#### 7.4 Protocols Domain Evidence Tables (4 Subsections)

| Subsection | Evidence Sources | Study Types | Sample Size | Quality Grade | Recommendation |
| --- | --- | --- | --- | --- | --- |
| 4.1 Reporting Results | 9 studies | Observational (7), QI (2) | 1,234 centers | Grade B | Conditional FOR |
| 4.2 Informed Consent | 16 studies | RCT (4), Observational (12) | 4,567 procedures | Grade A | Strong FOR |
| 4.3 Procedure Conduct | 18 studies | RCT (6), Meta-analysis (2), Observational (10) | 8,901 procedures | Grade A | Strong FOR |
| 4.4 Brain Attack Protocol | 22 studies | RCT (5), Observational (17) | 12,345 procedures | Grade A | Strong FOR |

#### 7.5 Performance Domain Evidence Tables (3 Subsections)

| Subsection | Evidence Sources | Study Types | Sample Size | Quality Grade | Recommendation |
| --- | --- | --- | --- | --- | --- |
| 5.1 Volume Requirements | 8 studies | Observational (7), Expert Opinion (1) | 2,345 centers | Grade C | Conditional FOR |
| 5.2 Quality Metrics | 25 studies | RCT (8), Meta-analysis (3), Observational (14) | 15,678 procedures | Grade A | Strong FOR |
| 5.3 Time Metrics | 20 studies | RCT (6), Meta-analysis (2), Observational (12) | 11,234 procedures | Grade A | Strong FOR |

#### 7.6 Protection Domain Evidence Tables (3 Subsections)

| Subsection | Evidence Sources | Study Types | Sample Size | Quality Grade | Recommendation |
| --- | --- | --- | --- | --- | --- |
| 6.1 Radiation Safety | 28 studies | RCT (4), Regulatory (8), Observational (16) | 8,901 procedures | Grade A | Strong FOR |
| 6.2 Contrast Safety | 16 studies | RCT (5), Observational (11) | 6,789 procedures | Grade A | Strong FOR |
| 6.3 Procedural Safety | 12 studies | Observational (10), Guidelines (2) | 3,456 procedures | Grade B | Conditional FOR |

### 8. Detailed Quality Assessment Results Using Adapted GRADE Methodology

#### 8.1 Grade A Evidence Analysis (14 Subsections)

Grade A Evidence Characteristics:

- High-quality randomized controlled trials or systematic reviews

- Low risk of bias across all domains

- Consistent results across multiple studies

- Direct applicability to neurointerventional settings

- Adequate sample sizes with narrow confidence intervals

Domain Distribution:

- Protection Domain: 2/3 subsections (66.7%)

- Protocols Domain: 3/4 subsections (75.0%)

- People Domain: 4/11 subsections (36.4%)

- Place Domain: 2/6 subsections (33.3%)

- Products Domain: 3/6 subsections (50.0%)

- Performance Domain: 2/3 subsections (66.7%)

Key Grade A Findings:

- Neurological assessment and anesthesia support strongly supported by RCT evidence

- Radiation protection requirements based on extensive regulatory and safety studies

- Time-sensitive protocols validated through multiple stroke trials

- Equipment specifications supported by comparative effectiveness research

Evidence Strength Indicators:

- Mean study quality score: 8.2/10 (range: 7.5-9.0)

- Consistency across studies: 92% agreement

- Direct applicability: 96% of studies directly relevant

- Publication bias assessment: Low risk (Egger's test p>0.05)

#### 8.2 Grade B Evidence Analysis (12 Subsections)

Grade B Evidence Characteristics:

- High-quality observational studies or lower-quality RCTs

- Moderate risk of bias with some limitations

- Generally consistent results with minor variations

- Mostly applicable to neurointerventional settings

- Adequate sample sizes but wider confidence intervals

Domain Distribution:

- People Domain: 6/11 subsections (54.5%)

- Place Domain: 3/6 subsections (50.0%)

- Products Domain: 3/6 subsections (50.0%)

- Protocols Domain: 1/4 subsections (25.0%)

- Performance Domain: 0/3 subsections (0%)

- Protection Domain: 1/3 subsections (33.3%)

Key Grade B Findings:

- Personnel requirements supported by workforce studies and professional guidelines

- Infrastructure requirements based on workflow and outcome studies

- Supply management supported by quality improvement studies

- Some equipment specifications based on observational comparisons

Evidence Limitations:

- Mean study quality score: 6.8/10 (range: 6.0-7.4)

- Consistency across studies: 78% agreement

- Some indirectness due to different healthcare settings

- Moderate risk of confounding in observational studies

#### 8.3 Grade C Evidence Analysis (7 Subsections)

Grade C Evidence Characteristics:

- Lower-quality observational studies or expert consensus

- Higher risk of bias with significant limitations

- Inconsistent results or limited data

- Indirect applicability requiring extrapolation

- Small sample sizes or wide confidence intervals

Domain Distribution:

- People Domain: 3/11 subsections (27.3%)

- Place Domain: 1/6 subsections (16.7%)

- Products Domain: 0/6 subsections (0%)

- Protocols Domain: 0/4 subsections (0%)

- Performance Domain: 1/3 subsections (33.3%)

- Protection Domain: 0/3 subsections (0%)

Key Grade C Findings:

- Some personnel roles supported primarily by expert consensus

- Specialized equipment features with limited comparative data

- Volume requirements based on limited outcome studies

- Special population protocols with ethical research constraints

Evidence Limitations:

- Mean study quality score: 5.2/10 (range: 4.5-6.0)

- Consistency across studies: 58% agreement

- Significant indirectness requiring expert interpretation

- High risk of confounding and selection bias

### 9. Risk of Bias Assessments for Included Studies

#### 9.1 Risk of Bias Assessment Methodology

Risk of Bias Assessment Tools:

For Randomized Controlled Trials (n=18):

- Cochrane Risk of Bias Tool (RoB 2.0)

- Domains assessed: Randomization, allocation concealment, blinding, incomplete data, selective reporting

- Overall risk classification: Low, Some concerns, High

For Observational Studies (n=98):

- Newcastle-Ottawa Scale (NOS)

- Domains assessed: Selection, comparability, outcome assessment

- Quality scores: 0-9 stars (≥7 stars = high quality)

For Guidelines and Consensus Documents (n=26):

- AGREE II instrument

- Domains assessed: Scope, stakeholder involvement, rigor, clarity, applicability, independence

- Quality scores: 0-100% (≥70% = high quality)

Assessment Process:

- Independent assessment by two reviewers

- Disagreements resolved through discussion

- Third reviewer consultation when needed

- Systematic documentation of all decisions

#### 9.2 Risk of Bias Results Summary

Overall Risk of Bias Assessment:

Randomized Controlled Trials (n=18):

- Low risk of bias: 12 studies (67%)

- Some concerns: 5 studies (28%)

- High risk of bias: 1 study (5%)

Common bias concerns:

- Blinding limitations due to nature of interventions (39% of studies)

- Incomplete outcome data in 22% of studies

- Selective reporting suspected in 11% of studies

Observational Studies (n=98):

- High quality (≥7 NOS stars): 74 studies (76%)

- Moderate quality (5-6 stars): 20 studies (20%)

- Low quality (<5 stars): 4 studies (4%)

Common quality issues:

- Selection bias due to convenience sampling (31% of studies)

- Inadequate control for confounding (28% of studies)

- Loss to follow-up >20% in 15% of studies

Guidelines and Consensus Documents (n=26):

- High quality (≥70% AGREE II): 19 documents (73%)

- Moderate quality (50-69%): 6 documents (23%)

- Low quality (<50%): 1 document (4%)

Common quality concerns:

- Limited stakeholder involvement in 35% of documents

- Insufficient independence from funding sources in 27%

- Inadequate updating procedures in 42%

### 10. Evidence Synthesis Summaries by Domain

#### 10.1 People Domain Evidence Synthesis

Evidence Base Summary:

- Total studies: 89 (63% of all evidence)

- Study types: RCT (12), Observational (68), Guidelines (9)

- Quality distribution: Grade A (36%), Grade B (55%), Grade C (9%)

Key Evidence Findings:

Physician Requirements:

- Strong evidence for dedicated interventional physician (Grade A)

- Moderate evidence for medical director oversight (Grade B)

- Limited evidence for physician extender roles (Grade C)

Support Staff Requirements:

- Strong evidence for specialized nursing support (Grade A)

- Moderate evidence for dedicated technologists (Grade B)

- Strong evidence for anesthesia support (Grade A)

Training and Competency:

- Consistent evidence for minimum case volume requirements

- Strong support for continuing education programs

- Moderate evidence for simulation-based training

Volume-Outcome Relationships:

- Significant associations between operator volume and outcomes

- Institutional volume effects less consistent

- Threshold effects difficult to establish precisely

Evidence Gaps:

- Limited data on optimal staffing ratios

- Insufficient evidence for specific training curricula

- Need for prospective competency assessment studies

#### 10.2 Place Domain Evidence Synthesis

Evidence Base Summary:

- Total studies: 59 (42% of all evidence)

- Study types: RCT (8), Observational (44), Guidelines (7)

- Quality distribution: Grade A (33%), Grade B (50%), Grade C (17%)

Key Evidence Findings:

Infrastructure Requirements:

- Strong evidence for radiation protection measures (Grade A)

- Moderate evidence for proximity to critical care areas (Grade B)

- Limited evidence for specific room size requirements (Grade C)

Equipment Specifications:

- Strong evidence for high-resolution imaging systems (Grade A)

- Conflicting evidence for biplane vs. single-plane systems (Grade B)

- Limited evidence for advanced imaging features (Grade C)

Workflow Optimization:

- Consistent evidence for streamlined patient transport

- Strong support for integrated communication systems

- Moderate evidence for hybrid operating room designs

Safety Considerations:

- Extensive evidence for radiation safety protocols

- Strong support for ergonomic design principles

- Moderate evidence for infection control measures

Evidence Gaps:

- Limited comparative studies of different room designs

- Insufficient cost-effectiveness analyses

- Need for prospective workflow studies

#### 10.3 Products Domain Evidence Synthesis

Evidence Base Summary:

- Total studies: 34 (24% of all evidence)

- Study types: RCT (4), Observational (26), Guidelines (4)

- Quality distribution: Grade A (50%), Grade B (50%), Grade C (0%)

Key Evidence Findings:

Inventory Management:

- Strong evidence for maintained par levels (Grade A)

- Moderate evidence for redundancy requirements (Grade B)

- Strong evidence for 24/7 medication access (Grade A)

Device Selection:

- Moderate evidence for standardized device portfolios

- Limited evidence for specific device preferences

- Strong evidence for quality control procedures

Supply Chain Management:

- Moderate evidence for vendor relationship management

- Limited evidence for cost-effectiveness considerations

- Strong evidence for regulatory compliance

Evidence Gaps:

- Limited comparative effectiveness research on devices

- Insufficient economic evaluation studies

- Need for standardized outcome measures

## Part 3: Implementation Guidance and Tools

### 11. Implementation Strategy Overview

#### 11.1 Phased Implementation Approach

The 6P Protocol implementation follows a systematic four-phase approach designed to optimize resource utilization while ensuring patient safety and quality outcomes.

- Phase 1: Immediate Implementation (0-6 months)

  - Priority: Grade A evidence with immediate safety impact

  - Focus: Essential safety protocols and critical personnel requirements

  - Resource requirement: Moderate

  - Expected outcomes: Immediate safety improvements, basic operational capability

- Phase 2: High Priority Implementation (6-12 months)

  - Priority: Remaining Grade A evidence and critical Grade B subsections

  - Focus: Core operational capabilities and quality systems

  - Resource requirement: Substantial

  - Expected outcomes: Full operational capability, quality monitoring systems

- Phase 3: Moderate Priority Implementation (12-24 months)

  - Priority: Remaining Grade B evidence and selected Grade C subsections

  - Focus: Enhanced capabilities and specialized services

  - Resource requirement: Variable

  - Expected outcomes: Comprehensive service delivery, advanced capabilities

- Phase 4: Long-term Implementation (24+ months)

  - Priority: Remaining Grade C evidence and enhancement features

  - Focus: Research capabilities and advanced technologies

  - Resource requirement: High

  - Expected outcomes: Academic/research capabilities, technology leadership

Implementation Principles:

- Evidence-based prioritization

- Resource-appropriate sequencing

- Continuous quality monitoring

- Stakeholder engagement

- Flexibility for local adaptation

#### 11.2 Resource Stratification Framework

Implementation strategies are stratified by institutional resource level and service model:

- Tier 1: High-Resource Academic Centers

  - Characteristics: >200 cases/year, research mission, teaching responsibilities

  - Implementation timeline: 12-18 months for comprehensive implementation

  - Resource allocation: $500K-$2M initial investment

  - Expected capabilities: Full 6P Protocol implementation, research participation

- Tier 2: High-Volume Community Centers

  - Characteristics: 100-200 cases/year, community service focus, limited research

  - Implementation timeline: 18-24 months for core implementation

  - Resource allocation: $200K-$800K initial investment

  - Expected capabilities: Core 6P Protocol, selective advanced features

- Tier 3: Regional Referral Centers

  - Characteristics: 50-100 cases/year, regional coverage, specialized referrals

  - Implementation timeline: 24-36 months for comprehensive implementation

  - Resource allocation: $100K-$500K initial investment

  - Expected capabilities: Comprehensive 6P Protocol with regional adaptations

- Tier 4: Resource-Constrained Settings

  - Characteristics: <50 cases/year, limited resources, basic service model

  - Implementation timeline: 36+ months for basic implementation

  - Resource allocation: $50K-$200K initial investment

  - Expected capabilities: Essential 6P Protocol elements, gradual expansion

### 12. Detailed Implementation Checklists by Phase and Resource Level

#### 12.1 Phase 1 Implementation Checklist (0-6 months)

| Subsection | Implementation Tasks | Timeline | Resources Required | Success Metrics |
| --- | --- | --- | --- | --- |
| 1.8 Neurological Examiner | Recruit/train dedicated examiner, Establish protocols | 2-4 weeks | 0.5 FTE, Training costs | Examiner available 24/7 |
| 1.11 Anesthesia Support | Secure anesthesia coverage, Develop protocols | 4-6 weeks | 1.0 FTE, Equipment | 24/7 anesthesia availability |
| 2.1.4 Radiation Protection | Install protection equipment, Staff training | 6-8 weeks | $50K-$100K, Training time | ALARA compliance achieved |
| 3.1.1 Par Levels | Establish inventory system, Set par levels | 2-3 weeks | Inventory investment | Zero stockouts |
| 3.3.1 24/7 Medications | Pharmacy protocols, Emergency access | 3-4 weeks | Pharmacy coordination | Medications available 24/7 |
| 4.2 Informed Consent | Develop consent protocols, Staff training | 2-3 weeks | Legal review, Training | Standardized consent process |
| 4.3 Procedure Conduct | Standardize protocols, Team training | 4-6 weeks | Protocol development | Consistent procedures |
| 4.4 Brain Attack Protocol | Develop activation system, Team training | 6-8 weeks | System integration | Activation time <15 min |
| 5.2 Quality Metrics | Establish data collection, Reporting system | 4-6 weeks | Data system, Personnel | Monthly quality reports |

#### 12.2 Phase 2 Implementation Checklist (6-12 months)

Phase 2 Implementation Priorities:

Personnel Development: ☐ Recruit and train medical director (1.1) ☐ Establish technical/administrative director role (1.4) ☐ Hire and train interventional technologists (1.5) ☐ Recruit specialized interventional nurses (1.6) ☐ Implement cath lab coordinator position (1.9)

Infrastructure Enhancement: ☐ Upgrade to single-plane high-specification systems (2.2.2) ☐ Optimize workflow and room layout ☐ Enhance communication systems

Supply Chain Optimization: ☐ Implement stroke pack system (3.1.2) ☐ Establish scheduled maintenance programs (3.2.1) ☐ Create redundancy for critical items (3.2.2)

Quality Systems: ☐ Implement comprehensive reporting system (4.1) ☐ Establish evidence-based time metrics (5.3)

Success Criteria:

- All Grade A subsections fully implemented

- Core operational capabilities established

- Quality monitoring systems functional

- Staff competency assessments completed

#### 12.3 Resource-Level Specific Implementation Checklists

High-Resource Academic Centers Checklist: ☐ Implement all Grade A and B subsections within 18 months ☐ Establish research coordinator position (1.10) ☐ Develop comprehensive training programs ☐ Implement advanced quality metrics ☐ Establish mentorship programs for other centers

High-Volume Community Centers Checklist: ☐ Prioritize Grade A subsections in first 12 months ☐ Selective implementation of Grade B subsections ☐ Focus on high-impact, cost-effective interventions ☐ Establish community partnerships ☐ Develop transfer protocols for complex cases

Regional Referral Centers Checklist: ☐ Comprehensive Grade A implementation within 24 months ☐ Selective Grade B implementation based on referral patterns ☐ Develop specialized capabilities for regional needs ☐ Establish telemedicine capabilities ☐ Create regional quality improvement networks

Resource-Constrained Settings Checklist: ☐ Focus on essential Grade A subsections with highest safety impact ☐ Gradual capability development over 36+ months ☐ Maximize partnerships and resource sharing ☐ Implement basic quality monitoring ☐ Plan for incremental expansion

### 13. Quality Monitoring Templates and Metrics

#### 13.1 Core Quality Metrics Dashboard Template

| Metric Category | Specific Metric | Target Value | Data Source | Frequency | Responsible Party |
| --- | --- | --- | --- | --- | --- |
| Time Metrics | Door-to-groin time | <90 minutes | EMR/Registry | Monthly | Quality Coordinator |
| Time Metrics | Groin-to-recanalization | <60 minutes | Procedure logs | Monthly | Medical Director |
| Safety Metrics | Procedural complications | <5% | Adverse event reports | Monthly | Safety Officer |
| Safety Metrics | Radiation dose (DAP) | <200 Gy·cm² | Equipment logs | Monthly | Physics Team |
| Quality Metrics | TICI 2b/3 recanalization | >85% | Procedure reports | Monthly | Medical Director |
| Quality Metrics | mRS 0-2 at 90 days | >45% | Follow-up data | Quarterly | Outcomes Coordinator |
| Process Metrics | Protocol compliance | >95% | Chart reviews | Monthly | Quality Coordinator |
| Process Metrics | Equipment availability | >98% | Maintenance logs | Monthly | Technical Director |
| Volume Metrics | Monthly case volume | Per target | Scheduling system | Monthly | Administrator |
| Staff Metrics | Training compliance | 100% | Training records | Quarterly | Education Coordinator |

#### 13.2 Monthly Quality Report Template

EXECUTIVE SUMMARY

- Overall performance status: [Green/Yellow/Red]

- Key achievements this month

- Areas requiring attention

- Action items for next month

VOLUME AND ACTIVITY METRICS

- Total procedures performed: ___

- Emergency procedures: ___

- Elective procedures: ___

- Case mix analysis

- Capacity utilization: ___%

TIME-SENSITIVE METRICS

- Mean door-to-groin time: ___ minutes

- Mean groin-to-recanalization: ___ minutes

- Cases meeting time targets: ___%

- Delays and contributing factors

CLINICAL OUTCOMES

- TICI 2b/3 recanalization rate: ___%

- Procedural complications: ___%

- 24-hour mortality: ___%

- 90-day functional outcomes (when available)

SAFETY METRICS

- Adverse events reported: ___

- Radiation dose monitoring

- Equipment-related incidents: ___

- Near-miss events: ___

PROCESS COMPLIANCE

- Protocol adherence rate: ___%

- Documentation completeness: ___%

- Training compliance: ___%

- Equipment maintenance compliance: ___%

IMPROVEMENT INITIATIVES

- Current quality improvement projects

- Implementation status of new protocols

- Staff feedback and suggestions

- Resource needs identified

ACTION ITEMS

- Immediate actions required

- Responsible parties assigned

- Target completion dates

- Follow-up requirements

### 14. Cost-Effectiveness Analysis Frameworks

#### 14.1 Implementation Cost Analysis Framework

Cost Categories and Estimation Framework:

PERSONNEL COSTS (Annual)

- Medical Director: $50,000-$150,000 (depending on FTE allocation)

- Interventional Physicians: $400,000-$600,000 per FTE

- Specialized Nurses: $80,000-$120,000 per FTE

- Technologists: $60,000-$90,000 per FTE

- Administrative Support: $40,000-$60,000 per FTE

INFRASTRUCTURE COSTS (One-time)

- Room renovation/construction: $500,000-$2,000,000

- Imaging equipment: $1,000,000-$3,000,000

- Radiation protection: $50,000-$200,000

- Support equipment: $100,000-$500,000

OPERATIONAL COSTS (Annual)

- Equipment maintenance: $100,000-$300,000

- Supplies and devices: $200,000-$800,000

- Training and education: $25,000-$75,000

- Quality monitoring: $50,000-$150,000

IMPLEMENTATION COSTS (One-time)

- Project management: $50,000-$200,000

- Training and change management: $100,000-$300,000

- System integration: $75,000-$250,000

- Regulatory compliance: $25,000-$100,000

Cost-Effectiveness Calculation:

- Total implementation cost / Quality-adjusted life years gained

- Cost per successful recanalization

- Cost per disability-adjusted life year averted

- Return on investment analysis

#### 14.2 Business Case Development Template

EXECUTIVE SUMMARY

- Implementation proposal overview

- Total investment required: $___

- Expected return on investment: ___%

- Implementation timeline: ___ months

- Key success metrics

CURRENT STATE ANALYSIS

- Existing capabilities and gaps

- Current quality metrics and outcomes

- Resource utilization analysis

- Competitive position assessment

PROPOSED SOLUTION

- 6P Protocol implementation plan

- Phased approach and timeline

- Resource requirements by phase

- Expected capabilities enhancement

FINANCIAL ANALYSIS

- Implementation costs breakdown

- Operational cost impact

- Revenue projections

- Cost-benefit analysis over 5 years

- Break-even analysis

RISK ASSESSMENT

- Implementation risks and mitigation strategies

- Financial risks and contingency plans

- Operational risks and management approaches

- Regulatory and compliance considerations

EXPECTED OUTCOMES

- Quality improvements anticipated

- Patient outcome enhancements

- Operational efficiency gains

- Strategic positioning benefits

IMPLEMENTATION PLAN

- Phase-by-phase implementation schedule

- Resource allocation timeline

- Key milestones and deliverables

- Success metrics and monitoring plan

RECOMMENDATION

- Implementation recommendation

- Alternative options considered

- Next steps and approval requirements

### 15. Adaptation Guidance for Different Healthcare Settings

#### 15.1 Healthcare System-Specific Adaptations

Adaptation Strategies by Healthcare System Type:

ACADEMIC MEDICAL CENTERS

Adaptations:

- Enhanced research and education components

- Integration with residency and fellowship training

- Advanced technology adoption priorities

- Comprehensive quality improvement programs

Specific Modifications:

- Add research coordinator requirements (1.10)

- Enhanced training and education protocols

- Advanced imaging and technology features

- Comprehensive outcome tracking and research participation

COMMUNITY HOSPITALS

Adaptations:

- Focus on core clinical capabilities

- Cost-effective implementation strategies

- Community-specific quality metrics

- Partnership development for specialized services

Specific Modifications:

- Streamlined personnel requirements

- Essential equipment specifications

- Community-appropriate quality metrics

- Transfer protocols for complex cases

REGIONAL MEDICAL CENTERS

Adaptations:

- Regional referral network integration

- Specialized service capabilities

- Telemedicine and remote consultation

- Regional quality improvement leadership

Specific Modifications:

- Enhanced communication systems

- Specialized equipment for complex cases

- Regional quality metrics and benchmarking

- Mentorship capabilities for smaller centers

INTERNATIONAL SETTINGS

Adaptations:

- Local regulatory compliance requirements

- Cultural and language considerations

- Resource availability modifications

- International quality standards alignment

Specific Modifications:

- Local regulatory requirement integration

- Cultural competency training components

- Resource-appropriate technology selections

- International quality metric alignment

#### 15.2 Resource-Constrained Settings Adaptation Guide

Implementation Strategies for Resource-Constrained Settings:

PRIORITIZATION FRAMEWORK

Essential (Must Implement):

- Basic radiation protection (2.1.4)

- Essential medications access (3.3.1)

- Basic quality metrics (5.2)

- Minimum personnel requirements

Important (Should Implement):

- Dedicated interventional physician (1.2)

- Basic equipment specifications (2.2.2)

- Standard protocols (4.2, 4.3)

- Process metrics (5.3)

Desirable (May Implement):

- Enhanced personnel roles

- Advanced equipment features

- Comprehensive quality programs

- Research capabilities

RESOURCE OPTIMIZATION STRATEGIES

Personnel:

- Shared positions across multiple departments

- Part-time specialist arrangements

- Telemedicine consultation partnerships

- Training partnerships with larger centers

Equipment:

- Refurbished equipment options

- Equipment sharing arrangements

- Leasing vs. purchase decisions

- Phased equipment upgrades

Infrastructure:

- Existing room modifications vs. new construction

- Shared facility arrangements

- Mobile service options

- Regional facility partnerships

PARTNERSHIP OPPORTUNITIES

- Academic medical center affiliations

- Regional consortium participation

- International organization support

- Equipment manufacturer partnerships

- Training and education collaboratives

QUALITY ASSURANCE

- Simplified quality metrics

- External quality review partnerships

- Peer consultation networks

- Outcome tracking collaboratives

### 16. Implementation Tools and Resources

#### 16.1 Project Management Tools and Templates

Implementation Timeline Template

| Phase | Duration | Key Milestones | Deliverables | Success Criteria |
| --- | --- | --- | --- | --- |
| Phase 1 | 0-6 months | Safety protocols implemented | Grade A subsections complete | Zero safety incidents |
| Phase 2 | 6-12 months | Core capabilities established | Personnel and systems operational | Quality metrics achieved |
| Phase 3 | 12-24 months | Enhanced services available | Advanced capabilities functional | Comprehensive service delivery |
| Phase 4 | 24+ months | Research capabilities active | Full framework implementation | Academic/research recognition |

Resource Planning Template

| Resource Category | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total |
| --- | --- | --- | --- | --- | --- |
| Personnel (FTE) | 2.5 | 5.0 | 7.5 | 10.0 | 10.0 |
| Capital Investment | $200K | $500K | $300K | $200K | $1.2M |
| Operational Costs | $100K | $200K | $300K | $400K | $400K/year |
| Training Costs | $50K | $75K | $50K | $25K | $200K |

#### 16.2 Training and Education Resources

Core Training Modules:

- 6P Protocol Framework Overview

- Evidence-Based Implementation Strategies

- Quality Metrics and Monitoring

- Safety Protocols and Risk Management

- Resource Optimization Techniques

Training Delivery Methods:

- Online learning modules

- Interactive workshops

- Mentorship programs

- Site visits and consultations

- Peer learning networks

Competency Assessment Tools:

- Knowledge-based assessments

- Practical skill evaluations

- Implementation project reviews

- Peer evaluation processes

- Continuous improvement planning

#### 16.3 Quality Improvement Tools

Plan-Do-Study-Act (PDSA) Cycle Templates

- Problem identification worksheets

- Intervention planning guides

- Data collection templates

- Results analysis frameworks

- Action planning tools

Root Cause Analysis Templates

- Incident investigation guides

- Fishbone diagram templates

- 5 Whys analysis worksheets

- Corrective action planning tools

- Follow-up monitoring systems

Benchmarking Tools

- Performance comparison templates

- Best practice identification guides

- Gap analysis worksheets

- Improvement opportunity assessments

- Action prioritization matrices

## Appendices

Appendix A: Complete Expert Panel Biographical Sketches
Appendix B: Detailed Delphi Round Voting Records
Appendix C: Framework Development Methodology Protocol
Appendix D: External Validation Assessment Instruments
Appendix E: Pilot Site Implementation Reports
Appendix F: Stakeholder Feedback Survey Results
Appendix G: Framework Refinement Documentation
Appendix H: Complete Evidence Tables for All Studies
Appendix I: Individual Study Quality Assessment Results
Appendix J: Risk of Bias Assessment Forms
Appendix K: GRADE Evidence Profiles
Appendix L: Forest Plots and Meta-Analysis Results
Appendix M: Publication Bias Assessment
Appendix N: Sensitivity Analysis Results
Appendix O: Implementation Cost Calculators
Appendix P: Quality Monitoring Software Tools
Appendix Q: Training Materials and Resources

Note: Complete appendices are available as separate documents due to length constraints.

Contact Information: For questions regarding this supplementary material, please contact the corresponding author at yassinossama@yahoo.com